## Instructions
EARNED VALUE MANAGEMENT — INSTRUCTIONS
Getting Started
1. Go to the 'EVM Analysis' sheet
2. Update project info: Project Name, Prepared By, Date, Current Period
3. Enter task names, WBS codes, and Budget at Completion (BAC) per task
4. Distribute each task's budget across periods (cols E-P)
Entering Actuals
5. Enter cumulative Actual Cost (AC) in row 17 for completed periods
6. Enter cumulative Earned Value (EV) in row 18 for completed periods
7. All performance metrics (rows 21-28) calculate automatically
Key Metrics
CV (Cost Variance) = EV - AC → positive is under budget
SV (Schedule Variance) = EV - PV → positive is ahead of schedule
CPI (Cost Performance Index) = EV / AC → >1.0 is good
SPI (Schedule Performance Index) = EV / PV → >1.0 is good
EAC (Estimate at Completion) = BAC / CPI
ETC (Estimate to Complete) = EAC - AC
VAC (Variance at Completion) = BAC - EAC
TCPI (To-Complete Performance Index) = remaining work / remaining budget
Color Coding
Blue font = editable input cells
Black font = formula/calculated cells
Green values = favorable (under budget / ahead of schedule)
Red values = unfavorable (over budget / behind schedule)

## EVM-Analysis
EARNED VALUE MANAGEMENT
Project: | Sample Construction Project |  | Prepared By: | Project Manager |  | Date: | 2026-03-19 |  | Status: | In Progress | Priority: | High
BUDGETED COST (PV) BY TASK
WBS | Task Name | BAC | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6 | Period 7 | Period 8 | Period 9 | Period 10 | Period 11 | Period 12
1.1 | Site Preparation | 4200 | 700 | 700 | 700 | 700 | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | Foundation | 5400 | 0 | 0 | 900 | 900 | 900 | 900 | 900 | 900 | 0 | 0 | 0 | 0
1.3 | Framing | 6000 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0
1.4 | Electrical | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 600 | 600 | 600 | 600
1.5 | Plumbing | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 500 | 500 | 1000
1.6 | Finishing | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1000 | 1500
TOTAL (BAC) |  | 25200 | 700 | 700 | 1600 | 1600 | 2600 | 2600 | 2500 | 3000 | 2100 | 2600 | 2100 | 3100
CUMULATIVE VALUES & PERFORMANCE
Cumulative PV (BCWS) |  |  | 700 | 1400 | 3000 | 4600 | 7200 | 9800 | 12300 | 15300 | 17400 | 20000 | 22100 | 25200
Actual Cost (AC/ACWP) |  |  | 750 | 1800 | 3200 | 5000 | 7500 | 10200 | 13500
Earned Value (EV/BCWP) |  |  | 600 | 1500 | 2800 | 4500 | 6800 | 9500 | 12800
PERFORMANCE METRICS
Cost Variance (CV) |  | = EV - AC | -150 | -300 | -400 | -500 | -700 | -700 | -700
Schedule Variance (SV) |  | = EV - PV | -100 | 100 | -200 | -100 | -400 | -300 | 500
CPI (Cost Performance) |  | = EV / AC | 0.8 | 0.83333 | 0.875 | 0.9 | 0.90667 | 0.93137 | 0.94815
SPI (Schedule Performance) |  | = EV / PV | 0.85714 | 1.0714 | 0.93333 | 0.97826 | 0.94444 | 0.96939 | 1.0407
EAC (Estimate at Completion) |  | = BAC / CPI | 31500 | 30240 | 28800 | 28000 | 27794.1176 | 27056.8421 | 26578.125
ETC (Estimate to Complete) |  | = EAC - AC | 30750 | 28440 | 25600 | 23000 | 20294.1176 | 16856.8421 | 13078.125
VAC (Variance at Completion) |  | = BAC - EAC | -6300 | -5040 | -3600 | -2800 | -2594.1176 | -1856.8421 | -1378.125
TCPI (To-Complete PI) |  | = (BAC-EV)/(BAC-AC) | 1.0061 | 1.0128 | 1.0182 | 1.0248 | 1.0395 | 1.0467 | 1.0598